## Sheet1
Agile Project Plan
Project Name | POINT OF SALE
Team Members | Coquilla,Angelica
De Claro, Jeelenee Jayson
Martinez, Kyle Matthew
Start Date | 2017-08-20
End Date | 2017-12-06
Overall Progress | 100%
Task Name | Responsible | Start | End | Days | Status
UI for the system | all members | 2017-08-20 | 2017-09-15 | 26 | Complete
Find Client | all members | 2017-08-21 | 2017-08-22 | 1 | Complete
Meet the Client | all members | 2017-08-23 | 2017-08-23 | 0 | Complete
Make Concept Map | all members | 2017-08-25 | 2017-08-25 | 0 | Complete
Meet with the groupmate | all members | 2017-08-30 | 2017-08-30 | 0 | Complete
Design for the UI | all members | 2017-09-04 | 2017-09-15 | 11 | Complete
Documentation | all members | 2017-09-13 | 2017-09-25 | 12 | Complete
Meeting | all members | 2017-09-15 | 2017-09-15 | 0 | Complete
UI (apply html and css) | all members | 2017-09-18 | 2017-10-02 | 14 | Complete
User Side | De Claro & Martinez | 2017-09-18 | 2017-09-25 | 7 | Complete
Admin Dashboard | Coquilla&De Claro | 2017-09-22 | 2017-09-29 | 7 | Complete
Meeting with Client | all members | 2017-10-01 | 2017-10-01 | 0 | Complete
Functionality | all members | 2017-10-04 | 2017-11-20 | 47 | Complete
Log in and Sign up | Martinez | 2017-10-06 | 2017-10-12 | 6 | Complete
Ticketing(entrance & walkin) | Martinez | 2017-10-06 | 2017-10-20 | 14 | Complete
Reciept(can print) | De Claro | 2016-10-23 | 2016-10-27 | 4 | Complete
Users(deactivate&activate) | Martinez&De Claro | 2017-10-30 | 2017-11-06 | 7 | Complete
Revenue(daily,weekly,monthly,yearly) | Coquilla& De Claro | 2017-10-28 | 2017-11-06 | 9 | Complete
History | Coquilla&Martinez | 2017-11-05 | 2017-11-13 | 8 | Complete
Reports | Coquilla | 2017-11-10 | 2017-11-15 | 5 | Complete
Documentation | all members | 2017-10-04 | 2017-11-19 | 46 | Complete
Meeting with Client | all members | 2017-11-19 | 2017-11-19 | 0 | Complete
Finalization(UI,Functional,Documentation) | all members | 2017-11-20 | 2017-12-05 | 15 | Complete
Functionality | Martinez | 2017-11-20 | 2017-12-01 | 11 | Complete
UI | De Claro | 2017-11-20 | 2017-12-04 | 14 | Complete
Documentation | Coquilla | 2017-11-20 | 2017-12-04 | 14 | Complete
Meetings with group members | all members | 2017-12-04 | 2017-12-04 | 0 | Complete
Present to the Client | all members | 2017-12-05 | 2017-12-05 | 0 | Complete